PREPARATION TIMELINE

| 4-6 weeks before | Meet with manager of participants to discuss expectations, content, follow-up and accountabilities. |
| --- | --- |
| 3 weeks before | Complete your agenda and customize your PowerPoint slides. A generic outline is available online (FISH!EventPPT.pptx). Invite your participants. Whether by email, in person or on paper, create a welcoming invitation to your event. There are two customizable invitations available online (NewHireInvite.docx and FISH!Invite.docx). |
| 2 weeks before | Talk through your agenda with someone who will be honest and helpful. Discuss any areas or activities that concern you. If your discussion partner is going to participate, enlist his or her help. Have proper audio-visual equipment arranged. - Video player and monitor or LCD projector and screen (for FISH! film and PowerPoint presentation). - Computer or laptop with PowerPoint software for PCs or Keynote software for Macs. - Speakers loud enough for the room and group size. (Regular computer speakers work with groups of up to ten people. For larger groups, you’ll want something bigger.) - Wireless lavaliere microphone if you are using a larger room with more than 20 people, or if you have a quiet voice. - Music player and speakers (a great way to channel the room’s energy). - Copy of FISH! film. - PowerPoint slides customized and ready. Other resources to have ready: - A participant workbook for each participant. - Music playlists. - Flip chart and markers. - Activity-specific materials (e.g., Let’s Make a Day cards and dry-erase markers). - Name tags or table tents. - FISH! pens. - Stuffed Pete the Perch. - Coffee, snacks, food, etc. - Give-aways. - Table supplies (markers, sticky notes, paper, etc.). - Table decorations (tablecloths, flowers, creative centerpieces, etc.). |
| 7 days before | Consider room setup. Round tables for six people are optimal. Everyone should be able to see the screen and hear the sound clearly. If you are using rectangular or square tables, arrange them in a way that creates an environment where participants sit around the table versus just facing straight ahead. |
| 4 days before | Run through your agenda, PowerPoint and make any last-minute changes. |
| 3 days before | Run through the list of tasks you delegated to be sure that everything is on track. (If there are numerous people helping and many details, consider a couple of weekly check-ins prior to the event.) |
| 1 day before | Set up the room and test all technical items (Video player, computer, projector, mic, etc.). |
| Evening before | Relax, you are going to be great. You’re helping your organization create a more engaging and satisfying workplace. Remember to focus on the goal and impact you wrote on page 10. |
| Day of event | Go for it! Be There, Play, Make Their Day and Choose Your Attitude as the group’s facilitator. |
| 1 week post | Send first of five follow-up emails (FollowUpEmails.docx). Refer to your Journey Map on page 101 for next steps or follow up with the participants’ manager to discuss their Journey Map and plan for ongoing conversations. |